## Exportoverzicht
Dit document is geëxporteerd vanuit Numbers. Elke tabel is omgezet in een Excel-werkblad. Alle andere objecten op elk Numbers-werkblad zijn op afzonderlijke werkbladen geplaatst. Het is mogelijk dat formuleberekeningen in Excel kunnen verschillen.
Naam Numbers-werkblad | Naam Numbers-tabel | Naam Excel-werkblad
Template Retrospective
| Tabel 1 | Template Retrospective
Template Backlog
| Tabel 1 | Template Backlog

## Template Retrospective
Sprint Retrospective | Iteration | TEMPLATE
Project
Group
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
Bike Carbon Calculator | Integrate Carbon Calculations | Robert | 3 | 3 | yes
Bike Carbon Calculator | Test the api functionality | Robert | 4 | 4 | yes
Provide the calculation option for the heat consumption and public transport features. | Make the calculators to calculate the carbon footprint for the heat consumption and public transport features. | Nick | 4 | 5 | no
Provide the calculation option for the heat consumption feature. | Study the carbon dioxide saved by lowering heat consumption and implementing the calculator. | Nick | 2 | 3 | yes | Static methods are to be local fields in the calculator, this has no changes to functionality whatshowever\.
Vegan Meal Carbon | Extend carbon calculations for localproduce, veganmeal and solarpanels | Jaron and Lee | 2 | 2 | yes
Change Client resource | Change the client side to have one main resource | Jaron and Lee | 4 | 5 | yes | Not merged yet due to merge conflicts
Add friends page | Design add friends gui and input constraints | Mayasa | 3 | 3 | yes
Finalize authentication | Connect authentication to the server and database system | Natalia | 4 | 7 | no | Merge conflicts have to be resolved and tests have to be done.
GUI Design | Do the design for dashboard | Irem | 5 | 8 | yes
Main Problems Encountered
Problem 1
Description
Reaction
Problem 2
Description
Reactions
Adjustments for next Sprint Plan

## Template Backlog
Sprint Backlog | Iteration | TEMPLATE
Project
Group
Amount of hours
Member
Estimated amount of hours
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)