## Template Retrospective
Sprint Retrospective | Iteration | TEMPLATE
Project
Group
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
Calculating the Carbon Footprint | Implementing the CarbonCalculator Class (after researching formulas) | Robert | 10 hours | 10 hours | Done
Development of a feature | “Buying local produce” feature | Natalia Struharova | 3 hours | 5 hours | No (missing tests)
Creating the GUI | Creating log-in page and main pages in JavaFX | Irem | 6 hours | 10 hours | Done
Creating a database connector | Lee Chen |  | 7 hours | 10 hours | No
Creating the Database Connector |  |  | 7 hours | 10 hours | No
Development of the "public transport" feature | Develop the server- and client-side of the "public transport" feature | Nick Ouwerkerk | 5 hours | 8 hours | No | Tests not finished yet and calculations still to be implemented
Main Problems Encountered
Problem 1
Description | Build problems when doing the GUI
Reaction
Problem 2
Description | Integrating Maven into the GUI Project
Reactions
Adjustments for next Sprint Plan

## Template Backlog
Sprint Backlog | Iteration | TEMPLATE
Project
Group
Amount of hours
Member
Estimated amount of hours
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)