## Template Retrospective
Sprint Retrospective | [5 empty] | Secretary: Natalia
Project
Group
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
Authentication | Implementing authentication mechanism | Natalia | 3 | 6+ | No | At first we were using Basic Auth, but after doing some research, the decision was made that we substitute it with JWT. Currently in testing.
Local Produce Feature | Developing client-server communication and learning to work with Mockito | Natalia | 4 | 9 | Yes | Initially problems with Mockito.
Bike Feature | Developing client-server communication for Biking feature | Natalia | 4 | 4 | Yes
Development of the public transport feature | Implement server- and client-side for the public transport feature | Nick | 2 | 2 | Yes | Was already close to be finished so it did not need much time anymore
Development of the home heat consumption feature | Implement server- and client-side for the home heat consumption feature | Nick | 4 | 3 | Yes | The foundation is rather similar to the other feature(s) so this did not need much time. Did have a few problems with the testing but those were resolved quickly.
Development of the database | Link the database with the server | Robert, Lee, Jaron | 3 | 3 | No
Development on the server connection | Test the database connection | Jaron | 4 | 3 | No
GUI | Create activity pages for the features and send info to the server | Irem | 5 | 4 | Yes
Sending Personal Data through the client | Deploy the DB and Glassfish servlet container on the online Server and link it with the server | Robert | 2 | 6 | Yes
Vegan Meal Feature | Implement the vegan meal feature client and server side and link them to the database | Robert | 4 | 15 | Yes
Main Problems Encountered
Problem 1
Description
Reaction
Problem 2
Description
Reactions
Adjustments for next Sprint Plan
1. Contribute more to GitLab.

## Template Backlog
Sprint Backlog | Iteration | TEMPLATE
Project
Group
Amount of hours
Member
Estimated amount of hours
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)