## Template Retrospective
Sprint Retrospective | [5 empty] | Secretary: Irem
Project
Group
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
Follow other persons | Clien/Server side of the follow persons feature | Robert and Natalia | 5 | 5 | Yes
Personal Info | See personal info | Robert and Natalia | 2 | 2 | Yes
Achievements | Get achievements from the server | Robert and Natalia | 2 | 2 | Yes
Statistics piechart | ServerSide | Robert and Natalia | 4 | 4 | Yes
Authentication | Link authentication with GUI | Robert and Natalia | 5 | 2019-08-07 | Yes
User experience | Link GUI | Robbert, Natalia and Irem | 10 | 15 | Yes
Session management | Implement a token management workflow | Natalia and Robert | 4 | 6 | Yes
Achievements GUI | Design achievements for the GUI | Natalia | 5 | 3 | Yes
Menu GUI | Design menu for the GUI | Natalia | 4 | 7 | Yes
Bages board | Design user badges board | Mayasa | 5 | 7 | No
Draft report | Make the draft report | Nick | 7 | 7 | No
Main Problems Encountered
Problem 1
Description
Reaction
Problem 2
Description
Reactions
Adjustments for next Sprint Plan
1. Contribute more to GitLab.

## Template Backlog
Sprint Backlog | Iteration | TEMPLATE
Project
Group
Amount of hours
Member
Estimated amount of hours
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)