## Template Retrospective
Sprint Retrospective | [5 empty] | Secretary: Nick
Project
Group
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
Carbon calculating | Add input filters | Robert | 2 | 2 | Yes
Statistics | Fix the piechart | Robert / Irem | 2 | 2 | Yes
Draft report | Make the draft report | Nick | 8 | 9 | Yes
Menu design | Add labels | Natalia | 1 | 1 | Yes
Authentication tests | Add valid tests for lastest authentication | Natalia | 1 | 2 | Yes
Assignment design | Adjust design and beautify | Natalia | 2 | 2 | Yes
Confirmation message | Add confirmation after user adds an activity | Mayasa | 3 | 4 | Yes
You page layout | Design layout for 'you' page | Mayasa | 2 | 2 | Yes
Fix the scoreboard page | Fix the style of the page when the user has less than 3 friends | Irem | 2 | 2 | Yes
Add the tip to the menu page | Add animation and tip to the menu | Irem | 4 | 4 | Yes
Achievements | Create achievements connection with the database | Jaron | 6 | 7 | No
Main Problems Encountered
Problem 1
Description
Reaction
Problem 2
Description
Reactions
Adjustments for next Sprint Plan

## Template Backlog
Sprint Backlog | Iteration | TEMPLATE
Project
Group
Amount of hours
Member
Estimated amount of hours
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)