## Template Retrospective
Sprint Retrospective | [5 empty] | Secretary: Irem
Project
Group
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
Database connection for LocalProduce and SolarPanels | Create a class SolarPanels and link SolarPanels and LocalProduce with the database. Tested both classes. | Jaron | 4 | 5 | Yes | Got errors for wrong file encoding, which ment I had to re-upload the class with the correct encoding
Database connection for Biker | link the Biker feature with the database + test | Lee | 2 | 2 | Yes
Vegan Meal feature | Requests from the gui to the server | Robert, Irem | 2 | 4 | Yes
Authentication | Implementing JWT for LocalEater GET Request | Natalia | 3 | 8 | Yes | Yet to be linked to the database and made universal.
Bike and local product pages | Design the GUI and connect it to the main controller | Mayasa | 2 | 3 | Yes
Screen Resizing in GUI | Enable the screen resizing in GUI | Irem | 5 | 8 | No | Because of the pane structure is used before the design has to be changed and still working on it.
Extend the features public transport and home heat consumption to be able to persist data | Update the client- and serverside of the public transport and home heat consumption features to be able to interact with the database | Nick | 4 | 5 | Yes | Resources can be changed to fit the needs of the features, but since these fields are not decided yet the resources have the standard layout
Main Problems Encountered
Problem 1
Description
Reaction
Problem 2
Description
Reactions
Adjustments for next Sprint Plan
1. Contribute more to GitLab.

## Template Backlog
Sprint Backlog | Iteration | TEMPLATE
Project
Group
Amount of hours
Member
Estimated amount of hours
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)